## Slide 1: BCDSS Sprint 3 Review & Sprint 4 Planning Meeting
May 31, 2016

## Slide 2: BCDSS – Sprint 3 Review & Sprint 4 Planning Attendance
Office SME |  | Name |  | Attendance
Veteran Health Administration Innovations Program |  |  |  | 
Innovation Coordinator | Heath A Forney |  | * | 
OSP Liaison | Edward L Wells |  |  | 
Product Owner | Elizabeth Wollin |  | * | 
OBPI Representative | Kaitlin Conron |  | * | 
Comp Services | Matthew Padula |  | * | 
Comp Services | Paul J Shute |  |  | 
SME | VILAYPHONG SENTHEP |  | * | 
OBPI Representative | Karla Leal |  | * | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh |  | * | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy |  | * | 
Pro Sphere (BCDSS) | Darrell Dorman |  | * | 
PWS (BCDSS) | David Teague |  |  | 
Pro Sphere (BCDSS) | Dominic Yeh |  | * | 
Pro Sphere (BCDSS) | Erik Rothwell |  |  | 
Pro Sphere (BCDSS) | Ganesh Panneer |  | * | 
Pro Sphere (BCDSS) | Jeffrey Bamba |  | * | 
Pro Sphere (BCDSS) | Rebecca Garcia DeJesus |  | * | 
Pro Sphere (BCDSS) | Vasudeva Rayapati |  | * | 

## Slide 3: BCDSS – Sprint 3 Review & Sprint 4 Planning Agenda
Objectives
Value Delivered
Challenges
Retrospective
Program Calendar
Sprint Forward

## Slide 4: BCDSS – Sprint 3 Review & Sprint 4 Planning Objectives - Value Delivered (Sprint 3)
Chart: 
Chart: 
Chart: 
Chart: 
Completed the development for the Login of all users - Rater, Modeling Agent, and Administrator
Gathered requirements for Modeling Agent, includes Model edit capabilities
Development work on the Rater’s Dashboard in progress
Wireframes for Modeling Agent in progress
Continue to do wireframe updates for Modeling Agent and Administrative Dashboard
Wrap up Logon/Logoff process
Start work on the Dashboard for Rater
Prioritization of User management process tasks
Prioritization of Role-based security tasks
Objectives
Value Delivered

## Slide 5: BCDSS – Sprint 3 Review & Sprint 4 Planning Challenges
Challenge
  There was a limit to number of concurrent remote connections to our BCDS sandbox environment within the FTL
Mitigation
  Put in a support ticket to up the number of allowable connections
    – Support ticket status Resolved with 10 concurrent connection
  On boarded another developer to overcome the single point failure.

## Slide 6: BCDSS – Sprint 3 Review & Sprint 4 Planning Metrics – Velocity
Chart: Velocity Chart
| BCDSS Sprint 0 | BCDSS Sprint 1 | BCDSS Sprint 2 | BCDSS Sprint 3 | BCDSS Sprint 4
Commited | 20 | 32 | 18 | 19 | 0
Completed | 12 | 14 | 19 | 12 | 0
Average: - Sprint Velocity 14

## Slide 7: BCDSS – Sprint 3 Review & Sprint 4 Planning Metrics – Number of Tasks
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 4 | 13 | 0

## Slide 8: BCDSS – Sprint 3 Review & Sprint 4 Planning Sprint 2 Retrospective
Chart: 
Chart: 
Chart: 
Chart: 
Single point failure – need back ups for Development roles
Fix Wi-Fi issues and plan to use VA Lync meetings
Things are going well, as per the plan
What Went Well
What Can Improve

## Slide 9: BCDSS – Sprint 3 Review & Sprint 4 Planning Sprint 3 Retrospective
Chart: 
Chart: 
Chart: 
Chart: 
Masud to get more involved in Wireframe
Pre discussion with CJ before the SME Meeting is good
SME Discussion on wireframes went well
Document Templates for Collaborative Dev Package
What Went Well
What Can Improve

## Slide 10: BCDSS – Sprint 3 Review & Sprint 4 Planning Program Calendar
Sprint 3
(5/30 - 6/10)
Sprint 5
(6/27 - 7/8)
Sprint 6
(7/11 - 7/22)
Sprint 4
(6/13 - 6/24)
5/27
6/24
Sprint 4
Completion
Sprint 3
Completion
Sprint 2
Completion
Legend
Completed Not Completed Future
6/10
Collaborative Deliverable
Package and VASIC 1
6/06
7/8
Sprint 5
Completion
7/22
Sprint 6
Completion
Collaborative Deliverable
Package and VASIC 2
Notes: Add brief notes about the Sprint deliverables in this section - Elizabeth

## Slide 11: BCDSS – Sprint 3 Review & Sprint 4 Planning Sprint Forward (Sprint 4)
Continue to work on the Dashboard for Rater
Prioritization of Role-based security tasks
Prioritization of User management process tasks

## Slide 12: BCDSS – Sprint 3 Review & Sprint 4 Planning Questions
?

## Slide 13
Thank you!