## Slide 1: Sprint 11 Review & Sprint 12 Planning
October 3rd 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Casey Curry | *
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | *
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | 
Comp Services | Paul J Shute | *
OSP Liaison | Sarah Wear | 
OBPI Representative | Sasha Gillian | *
SME | VILAYPHONG SENTHEP | *
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Ellen Rosen (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
Pro Sphere (BCDSS) | Darrell Dorman | 
PWS (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Dominic Yeh | 
Pro Sphere (BCDSS) | Erik Rothwell | *
Pro Sphere (BCDSS) | Ganesh Panneer | 
Pro Sphere (BCDSS) | Jeffrey Bamba | 
Pro Sphere (BCDSS) | Masud Habib | *
Pro Sphere (BCDSS) | Vasudeva Rayapati | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 11)
Objectives | Value Delivered
Complete Modeling engine database structure Implementation of Modeling engine web service and integration framework design Develop SOAP based web service for the Modeling Engine implementation using Java, Jax-WS APIs Configure SoapUI in local and FTL environment Create mock service using SOAPUI | Completed Modeling engine database structure Developed SOAP based web service for the Modeling Engine Configured SoapUI in local and FTL environments Completed the mock service using SoapUI
Requirements Updates | Accept/Reject (Agree/Disagree) functionality
FTL Deployment | Code updates from Sprint 11 & 12 will be deployed into Development and Test environments by the end Sprint 12.

## Slide 5: Challenges
Temporary loss of connectivity to FTL sand box

## Slide 6: Metrics – Velocity
Chart: Velocity Chart – based on Story points
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15 | BCDSS Sprint 16 | BCDSS Sprint 17
Commited | 8 | 22 | 25 | 0 | 0 | 0 | 0 | 0 | 0
Completed | 23 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 7: Metrics – Number of Tasks
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 2 | 26 | 0

## Slide 8: Sprint 11 Retrospective
What went well?
Ground work for the Modeling Engine Design / Framework - is laid out and ready
Process flow / Documentation of change request is going in right direction
Document updates for CDP were delivered on time
What can Improve?
Set Goals / Expectations before the start of the sprint
Do the necessary document updates then and there - rather than waiting until the end of the month
Everyone needs to be attentive and be an active participant in the internal calls/discussions
To Include a slide which will give an updated on the overall project progress

## Slide 9: Program Calendar
Sprint 10
(9/5 - 9/16)
9/16
10/14
Sprint 12
Completion
Sprint 11
Completion
Sprint 10
Completion
Legend
Completed Not Completed Future
9/30
Collaborative Deliverable
Package and VASIC 5
9/23
10/28
Sprint 13
Completion
11/11
Sprint 14
Completion
Collaborative Deliverable
Package and VASIC 6
Sprint 11
(9/16 - 9/30)
Sprint 12
(10/3 - 10/14)
Sprint 13
(10/17 - 10/28)
10/21
Sprint 14
(10/31 - 11/11)

## Slide 10: Sprint Forward (Sprint 12)
Modeling engine components development.
Modeling web service implementation.
Load DDM Data to new data model.
To Begin gathering reporting requirements.

## Slide 11: Questions
?

## Slide 12
Thank you!