## Slide 1: Sprint 12 Review & Sprint 13 Planning
October 17th 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Samantha Hamilton | *
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | *
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | *
Comp Services | Paul J Shute | 
OSP Liaison | Sarah Wear | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | 
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Ellen Rosen (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
Pro Sphere (BCDSS) | Darrell Dorman | *
PWS (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Dominic Yeh | *
Pro Sphere (BCDSS) | Erik Rothwell | *
Pro Sphere (BCDSS) | Ganesh Panneer | *
Pro Sphere (BCDSS) | Jeffrey Bamba | 
Pro Sphere (BCDSS) | Masud Habib | *
Pro Sphere (BCDSS) | Vasudeva Rayapati | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 12)
Objectives | Value Delivered
Modeling engine components development. Modeling web service implementation. Load DDM Data to new data model. | Made progress on the Implementation of Modeling engine web service and integration framework design Developed Hibernate components for the database object relation mapping Populated the data into the updated BCDSS data model
Requirements Updates To Begin gathering reporting requirements. | Conducted initial reporting requirements among internal team members Conducted a status briefing during the weekly SME meeting
FTL Deployment | 

## Slide 5: Challenges
Web service client – WSDL interaction
  Reason: Web service security
  Conclusion: After disabling the security layer, development team were able to publish the endpoint.

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15 | BCDSS Sprint 16 | BCDSS Sprint 17
Commited | 8 | 22 | 25 | 21 | 0 | 0 | 0 | 0 | 0
Completed | 23 | 19 | 17 | 20 | 0 | 0 | 0 | 0 | 0

## Slide 7: Metrics – Number of Tasks
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 1 | 20 | 0

## Slide 8: BCDSS – Progress Update
Data Tier
Web Tier
User Interface (Angular.Js, HTML, CSS)
Application Tier
Business Logic Services
Tech Services
Data Access Services
Data Transformation
Model Repository
Role Based Security
Models
Rules
Rating Data
Modeling Results
Users
Security
Other Meta data

## Slide 9: Sprint 12 Retrospective
What went well?
Adding more development resources will help the team’s progress
What can Improve?
Utilize JIRA effectively by adding more clarity to the work items (which is epics, stories and sub-tasks)
Communicate effectively during the stand-up
Progress update slide to have more information

## Slide 10: Program Calendar
Sprint 10
(9/5 - 9/16)
9/16
10/14
Sprint 12
Completion
Sprint 11
Completion
Sprint 10
Completion
Legend
Completed Not Completed Future
9/30
Collaborative Deliverable
Package and VASIC 5
9/23
10/28
Sprint 13
Completion
11/11
Sprint 14
Completion
Collaborative Deliverable
Package and VASIC 6
Sprint 11
(9/16 - 9/30)
Sprint 12
(10/3 - 10/14)
Sprint 13
(10/17 - 10/28)
10/21
Sprint 14
(10/31 - 11/11)

## Slide 11: Sprint Forward (Sprint 13)
Regenerate Hibernate components for the database updates – identified while data load.
Develop Knee ratings calculation
Fix the web service – security layer and publish endpoint
Continue to gather reporting requirements.

## Slide 12: Questions
?

## Slide 13
Thank you!