## Slide 1
BCDSS Weekly Status Report
PM: Erik Rothwell
ACCOMPLISHMENTS
Conducted Scrum Meetings, Peer Code Review, Sprint Review & Planning Meeting.
Making progress on the Implementation of Modeling engine web service and integration framework design
  To Develop Hibernate components for the database object relation mapping
  To Develop Knee aggregate contention and decision components
  To Populate data into the updated BCDSS data model
NEXT STEPS
Sprint 12 continuation
  Complete Hibernate components for the database object relation mapping
  Complete Knee aggregate contention and decision components
Complete Data load in DDM for the updated BCDSS data model
Conduct Internal review sessions for Reporting Requirements
Conduct Pilot planning
ISSUES
Onboarding
  Evan Webber (Technical Writer) – VA Onboarding - in progress
    Completed Finger print appointment on Monday (9/26)
  Pending CAG Access
    Darrell Dorman
    Ganesh Panneer
      Eric Hickam and others working to get a resolution
      Followed up with Eric H on 10/06/2016
RISKS / Technical Issues
Web service client – WSDL interaction is throwing an exception
    Likely reason: configuration mismatch