## Slide 1: BCDSS Sprint 6 Review & Sprint 7 Planning Meeting
July 25 2016

## Slide 2: BCDSS – Sprint 6 Review & Sprint 7 Planning Attendance
Office SME |  | Name |  | Attendance
Veteran Health Administration Innovations Program |  |  |  | 
Innovation Coordinator | Heath A Forney |  |  | 
OSP Liaison | Edward L Wells |  |  | 
Product Owner | Elizabeth Wollin |  | * | 
OBPI Representative | Kaitlin Conron |  | * | 
Comp Services | Matthew Padula |  | * | 
Comp Services | Paul J Shute |  |  | 
SME | VILAYPHONG SENTHEP |  | * | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh |  | * | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy |  | * | 
Pro Sphere (BCDSS) | Darrell Dorman |  | * | 
PWS (BCDSS) | David Teague |  |  | 
Pro Sphere (BCDSS) | Dominic Yeh |  | * | 
Pro Sphere (BCDSS) | Erik Rothwell |  |  | 
Pro Sphere (BCDSS) | Ganesh Panneer |  | * | 
Pro Sphere (BCDSS) | Jeffrey Bamba |  | * | 
Pro Sphere (BCDSS) | Masud Habib |  | * | 
Pro Sphere (BCDSS) | Rebecca Garcia DeJesus |  |  | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *

## Slide 3: BCDSS – Sprint 6 Review & Sprint 7 Planning Agenda
Objectives
Value Delivered
Challenges
Demonstration
Retrospective
Program Calendar
Sprint Forward

## Slide 4: BCDSS – Sprint 6 Review & Sprint 7 Planning Objectives - Value Delivered (Sprint 6)
Chart: 
Chart: 
Chart: 
Chart: 
Modeling Agent - Dashboard
Data object structure for Modelling Agent’s dashboard.
Data object query for Modelling Agent’s dashboard.
Requirements
Gathered Requirements for User Managements
Created Mockups of the user management (add, edit, activate/deactivate users...) and reviewed with SMEs
Rater’s Dashboard Wireframe
Updated the mockups into a HTML file to be shared with Business and SMEs to have hands on experience of the Rater’s workflow (except Reports)
Documentation
Completed the review comments from the previous deliverable
Documentation update for July – Collaborative development package
User stories
Broke the larger functional user stories in to smaller stories, to ensure the committed stories are completed in each sprint
Continue to work on Modeling & Rater’s Dashboard for Implementing Search and Model selection functionalities.
Gather requirements around Administrator Dashboard
Objectives
Value Delivered

## Slide 5: BCDSS – Sprint 6 Review & Sprint 7 Planning Challenges
Challenge
  Inconsistent Data base schema – updates
Mitigation

## Slide 6: BCDSS – Sprint 6 Review & Sprint 7 Planning Metrics – Velocity
Chart: Velocity Chart – based on Story points
| BCDSS Sprint 0 | BCDSS Sprint 1 | BCDSS Sprint 2 | BCDSS Sprint 3 | BCDSS Sprint 4 | BCDSS Sprint 5 | BCDSS Sprint 6
Commited | 20 | 32 | 18 | 19 | 25 | 18 | 19
Completed | 12 | 14 | 19 | 12 | 16 | 18 | 12

## Slide 7: BCDSS – Sprint 6 Review & Sprint 7 Planning Metrics – Number of Tasks
Chart: Number of TASKS
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 4 | 19 | 0

## Slide 8: BCDSS – Sprint 6 Review & Sprint 7 Planning Sprint 6 Retrospective
Chart: 
Chart: 
Chart: 
Chart: 
Include an overall objective in a slide, which will help the audience to understand where we stand on the progress.
To Include the Revision History and hyperlinks for that updated section in all the document updates.
Easy to follow and very clear.
What Went Well
What Can Improve

## Slide 9: BCDSS – Sprint 6 Review & Sprint 7 Planning Program Calendar
Sprint 6
(7/11 - 7/22)
7/22
8/19
Sprint 8
Completion
Sprint 7
Completion
Sprint 6
Completion
Legend
Completed Not Completed Future
8/5
Collaborative Deliverable
Package and VASIC 3
7/29
9/2
Sprint 9
Completion
9/16
Sprint 10
Completion
Collaborative Deliverable
Package and VASIC 4
Sprint 7
(7/25 - 8/5)
Sprint 8
(8/8 - 8/19)
Sprint 9
(8/22 - 9/2)
8/26
Notes: Add brief notes about the Sprint deliverables in this section - Elizabeth

## Slide 10: BCDSS – Sprint 6 Review & Sprint 7 Planning Sprint Forward (Sprint 7)
Continue to work on Modeling Agent – Dashboard
Define rules of behavior for each of BCDSS – user roles
  Administrator
  Modeling Agent &
  Rater

## Slide 11: BCDSS – Sprint 6 Review & Sprint 7 Planning Questions
?

## Slide 12
Thank you!