## CLIN 002AB BCDSS RTM
BCDSS Requirements Traceability Matrix Report (CLIN# 0002AB / February Iteration )
Project | K | Functional Requirement Statement | User Story ID | User Story Summary | Story Status | Test Case # | Testing status
BCDSS | 5.2.1 | As Creation Requirement I want to Provide a data management environment, structure and mechanism So I can conduct pattern analysis of historical claims data to identify predictive characteristics that form the basis of new predictive models | BCDSS-83 | As a dev, I want to develop a data mechanism containing data structure & environment as a creation requirement to conduct pattern analysis of historical claims to identify predictive characteristics that form the basis of new predictive models. | New |  | Not started
BCDSS | 5.2.5 | As Modeler I want to Model Results Records So I can Review Exceptions List | BCDSS-82 | As a modeler I want access to model results records so I can review exceptions list. | New |  | Not started
BCDSS | 5.2.7 | As Modeler I want to Select results sets from those available So I can Review selected results sets | BCDSS-81 | As a modeler I want to review the selected result sets so I can easily maintain the output/results from the model. | New |  | Not started
BCDSS | 5.2.7 | As Modeler I want to Select Results Sets So I can Select results sets from those available in system | BCDSS-80 | As a modeler I want the authority to select result sets from those available in the system. | New |  | Not started
BCDSS | 5.2.6 | As Modeler I want to Model Results Records So I can Select what solution is supposed to do | BCDSS-79 | As a modeler I want to select what solution is supposed to help so I can keep maintenance of model results records. | New |  | Not started
BCDSS | 5.2.2 | As Modeler I want to Target Claims Data Records So I can Select which Target Claims Data form those available | BCDSS-78 | As a modeler I want to select which target claims data records from those available so I can compare the accuracy of results. | New |  | Not started
BCDSS | 5.2.3 | As Modeler I want to Use System to execute model against claims data So I can Execute selected model against selected claims data | BCDSS-77 | As a modeler I want to use the system to execute model against claims data so I can compare the accuracy of results. | New |  | Not started
BCDSS | 5.2.3 | As Modeler I want to Select Model So I can Select appropriate model from those available | BCDSS-76 | As a modeler I want to have authorization so I can select the appropriate model from those that are available. | New |  | Not started
BCDSS | 5.2.7 | As Modeler I want to Select Destination and Format So I can Customize Output/ Results | BCDSS-75 | As a modeler I want to select destination and format so I can customize output/results. | New |  | Not started
BCDSS | 5.2.6 | As Modeler I want to Select Target Claims Data So I can Run Model with available options against target set of claims | BCDSS-74 | As a modeler I want to have select target claims data so I can run model with available options against target set of claims. | New |  | Not started
BCDSS | 5.2.1 | As ModelAgent I want to Authorization So I can Make temporary pre-verification models | BCDSS-73 | As a modeling agent I want authorization so I can make temporary pre-verification models. | New |  | Not started
BCDSS | 5.2.6 | As Model Agent I want to Authorization So I can Format Verification Records | BCDSS-72 | As a modeling agent I want authorization so I can format verification records. | New |  | Not started
BCDSS | 5.2.1 | As Modeling Agent I want to Authorization So I can Model Repository Records | BCDSS-71 | As a modeling agent I want authorization so I can manage the model repository records. | New, |  | Not started
BCDSS | 5.2.6 | As Model Agent I want to Authorization So I can Delete Models from the Repository | BCDSS-70 | As a modeling agent I want authorization so I can delete models from the repository (Does the government want this or an archival function?) | New |  | Not started
BCDSS | 5.2.6 | As Model Agent I want to Authorization So I can Make Targeted Edits to existing Models | BCDSS-69 | As a modeling agent I want authorization so I can make targeted edits to existing models. | New |  | Not started
BCDSS | 5.2.6 | As Modeling Agent I want to Authorization So I can Add Models that conform to modeling repository | BCDSS-68 | As a modeling agent I want authorization to add models that conform to modeling repository so I can maintain the model. | New |  | Not started
BCDSS | 5.2.6 | As Administrator I want to Operate/Use System So I can Cofirm Compliance of New Models What is compliance? | BCDSS-67 | As a modeling agent I want to operate and use system so I can insure new models conform to specifications. | New |  | Not started
BCDSS | 5.2.4 | As Administrator I want to Hand Enter Directory Data So I can Portfolio and Target Directory Data would be hand entered | BCDSS-66 | As an administrator I want to manually upload data so I can manage portfolio and target directory data. | Deleted |  | Not started
BCDSS | 5.2.5 | As Administrator I want to Manage System So I can Manage Transaction Data that would be system generated | BCDSS-65 | As an administrator I want to manage system generated transaction data so I can maintain policy. | New |  | Not started
BCDSS | 5.2.6 | As Administrator I want to Add/ Create/ Manage User Profiles So I can Hand enter and manage the few User Profiles | BCDSS-64 | As an administrator I want to add, create, and manage user profile so I can manually manage the user profiles. | New |  | Not started
BCDSS | 5.2.1 | As Administrator I want to Author/ Create/ View Target Directories So I can Manage System | BCDSS-63 | As an administrator I want to authorize, create, and view target directories so that I can manage the system | New |  | Not started
BCDSS | 5.2.5 | As Administrator I want to Author. Develop. View Formats So I can Manage System | BCDSS-62 | As an administrator I want to develop and view formats so I can manage the system | New |  | Not started
BCDSS | 5.2.7 | As Administrator I want to Author/ Develop/ View Pre-Defined Reports So I can Manage System | BCDSS-61 | As an administrator I want rights within the system to all user's documents as the author and editor so I can manage the system | New |  | Not started
BCDSS | 5.2.3 | As Administrator I want to View Portfolio Data What is portfolio data So I can Manage System | BCDSS-60 | As an administrator I want to view the portfolio data so I can manage the system. | Deleted |  | Not started
BCDSS | 5.2.4 | As Administrator I want to Control/ View User Transaction Data So I can Manage System | BCDSS-59 | As an administrator I want to control and view user transaction data so I can manage the system. | New |  | Not started
BCDSS | 5.2.7 | As Administrator I want to control output formats/ domains So I can manage where the modeling results data is output and in what format(s). | BCDSS-58 | As an administrator I want to control output formats and domains so I can manage where the modeling results data is output and in what format. | New |  | Not started
BCDSS | 5.2.2 | As Administrator I want to Manage Target Data Sets So I can control what target data sets are available to users. | BCDSS-57 | As an administrator I want to control specific input domains so I can manage what target data sets are available to users, where they are available to the user, where the user is to direct them, and to create a specific directory for user to reference. | New (Revised) |  | Not started
BCDSS | 5.2.1 | As Administrator I want to control/ determine user profiles So I can manage their access/ privileges/ rights | BCDSS-56 | As an administrator I want to assign and control user profiles so that I can manage their access, privileges, and rights. | New |  | Not started
BCDSS | 5.2.7 | As Output Format I want to Output in multiple formats So I can Allow integration with existing or future claims processing solutions and the relevant eFolder | BCDSS-55 | As a rater I want output in multiple formats so integration with existing or future claims processing solutions and the relevant eFolder is always easy. | New |  | Not started
BCDSS | 5.2.7 | As Rating Determination Content I want to Output the rating, relevant claims data and analytical basis (or model) So I can Determine the rating | BCDSS-54 | As a rater I want the rating determination content to output the rating and relevant claims data through an analytical basis (model) so I can determine the claim rating. | New |  | Not started
BCDSS | 5.2.7 | As Administrator Is this a role or an admin function. Is this performance tuning I want information on system performance. So I can understand the health of the solution at any time. | BCDSS-53 | As an Administrator I want the content of the system's output to have alternatives so I can see session results. | New (Revised) |  | Not started
BCDSS | 5.2.7 | As System Output Content I want to Output Alternatives So I can See System Performance | BCDSS-52 | As a backend user, I want output alternatives so I can monitor/improve system performance for users. | New |  | Not started
BCDSS | 5.2.6 | As Output Control I want to UI Control So I can Select pre-defined outputs, format and destination of output | BCDSS-51 | As a user, I want to have all output control so I can select pre-defined outputs, formats, and destination of output. | New |  | Not started
BCDSS | 5.2.6 | As Administrative User I want to Ability to Administer the BCDSS remotely So I can | BCDSS-50 | As an administrative user I want to administer the BCDSS remotely so I can fix problems at any time. | New |  | Not started
BCDSS | 5.2.6 | As User I want to understand the role and associated functions of that role So I can perform my specific job | BCDSS-49 | As a backend user I want to take time to understand my role and functions specific to me so I can preform my job properly and efficiently | New |  | Not started
BCDSS | 5.2.6 | As User I want to access the BCDSS remotely So I can use the system for telework. | BCDSS-48 | As a backend user I want to access the BCDS SharePoint and all other documents remotely so I can work where convenient if I cannot make it into office | New (Revised) |  | Not started
BCDSS | 5.2.3 | As Store Requirement I want to Store User Control/ Transaction Data So I can Support HLR 2.4.1 | BCDSS-47 | As a backend user I want to store user control and transactional data so I can compare modeling results relative to historical rating result. | New |  | Not started
BCDSS | 5.2.5How much and how long? TBD- For discussion | As Store Requirement I want to Store Results Data So I can Support HLR 2.2.1 and 2.2.2 | BCDSS-46 | As a backend user, I want to store resulting claims data so I can ensure conformance to standards prior to injection and select target claim data for conformance. | New (Revised) |  | Not started
BCDSS | 5.2.3 | As Store Requirement I want to Store Target Claims Data So I can Support HLR 2.1.4 and 2.1.5 | BCDSS-45 | As a backend user, I want to store target claims data so I can ensure conformance to standards prior to ingestion and select target claim data for conformance. | New (Revised) |  | Not started
BCDSS | 5.2.1 | As Store Requirement I want to Store new models So I can Support HLR 3.1.1 and 3.1.2 | BCDSS-44 | As a backend user, I want to store new models after testing so I can keep records of historical and new patterns, as well as, improving future modeling efforts. | New |  | Not started
BCDSS | 5.2.7 | As Test Requirement I want to Test Modeling Results So I can Support requirement for HLR 2.3.1 and 2.3.2 | BCDSS-43 | As a backend user, I want to test new models so I can provide specific knee ratings and provide ear specific ratings. | New |  | Not started
BCDSS | 5.2.1 | As Test Requirement I want to Test New Models So I can Support requirements for HLR 2.1.2 and 2.1.5 | BCDSS-42 | As a backend user, I want to test new models so I can ensure conformance to standards prior to injection and select target claim data for conformance. | New |  | Not started
BCDSS | 5.2.1 | As Creation Requirement I want to Provide a means to what? So I can construct, configure, populate and temporally store new predictive models | BCDSS-41 | As a backend user, I want to develop an environment for data as a creation so I can construct, configure, populate, and store new predictive models. | Deleted |  | Not started
BCDSS | 5.2.6 | As Edit I want to UI control So I can edit/ revise existing predictive models | BCDSS-40 | As a backend user I want to have UI control so I can edit/revise existing predictive models manually. | New |  | Not started
BCDSS | 5.2.5 | As Store Requirement I want to Automatically store user transaction and results data So I can provide metric based reporting | BCDSS-39 | As a backend user, I want to create storage that automatically stores user transactions and results so I can provide metric based reporting. | New |  | Not started
BCDSS | 5.2.2 | As Rating Determination I want to retrieve necessary data from the target claim set So I can apply predictive models to forecast future ratings | BCDSS-38 | As a backend user, I want to retrieve necessary data within the target claim set from the rating determination matrix so I can apply predictive models to forecast future ratings . | New |  | Not started
BCDSS | 5.2.2 | As Test Requirement I want to Automatically retrieve selected target claims data and corresponding modeling results So I can support testing analysis | BCDSS-37 | As a backend user, I want to automatically retrieve selected target claims data and corresponding modeling results as a test requirement so I can see if outcome supports testing analysis. | New |  | Not started
BCDSS | 5.2.6 | As Test Requirement I want to UI Control for selection of target claims data So I can compare modeling results relative to historical rating result | BCDSS-36 | As a backend user, I want UI Control for selection of target claims data as a test requirement so I can compare modeling results relative to historical rating result. | New |  | Not started
BCDSS | 5.2.5 | As Rating Determination I want to determine whether an existing model is applicable to conditions/issues within the target claims data So I can ensure models are applied to applicable claims | BCDSS-35 | As a backend user, I want to create a filter within the rating determination matrix to determine whether an existing model is applicable to conditions within the target claims data so I can ensure the appropriate model is applied to applicable claims. | New |  | Not started
BCDSS | 5.2.5 | As Rating Determination I want to Capability to determine which conditions cannot be rated So I can provide a information to rater on unrated conditions | BCDSS-34 | As a backend user, I want to install the capability to determine which conditions cannot be rated within the rating determination matrix within the platform so I can provide a rejection record. | New |  | Not started
BCDSS | 5.2.5 Do we want to say compute or predict | As Rating Determination I want to compute the calculated rating for ear related disability condition (or issue) So I can provide ear specific rating | BCDSS-33 | As a backend user, I want to assign the calculated rating for ear related disabilities to a rating determination matrix within the platform so I can provide ear specific ratings via the model. | New (Revised) |  | Not started
BCDSS | 5.2.5 What are we saying here. Sounds like we are using BCDS to predict when or if a veteran will file a future request for increase? Our focus is on predicting the rating of a current request for increase or target claim. If the former this is out of scope or would go in backlog. If the latter, should rephrase | As Rating Determination I want to calculate the future rating for ear related disability conditions (issues) based on claims data So I can predict the rating for a supplimental claim for increase. | BCDSS-32 | As a backend user, I want to create a rating determination that will calculate future ratings for ear related disabilities as the issues grow based on original data so I can eliminate the need for future claims and adjustments | New (Revised) |  | Not started
BCDSS | Original HLR 2.3.1 | As Rating Determination I want to assign the calculated rating for knee related disability condition (or issue) So I can provide knee specific rating | BCDSS-31 | As a backend user, I want to assign the calculated rating for knee related disabilities to a rating determination matrix within the platform so I can provide specific knee ratings via the model. | New |  | Not started
BCDSS | Original HLR 2.3.1 Same as previous | As Rating Determination I want to calculate the future rating for knee related disability conditions (issues) based on claims data So I can determine a rating for a supplimental claim increase. | BCDSS-30 | As a backend user, I want to create a rating determination that will calculate future ratings for knee related disabilities as the issues grow based on original data so I can eliminate the need for future claims and adjustments. | New (Revised) |  | Not started
BCDSS | 5.2.6 | As Populate Requirement I want to Separate the modeling logic from the platform code (whether an algorithm, multi-dimensional array) or other So I can simplify maintenance of both the platform and the models | BCDSS-29 | As a backend user, I want to separate modeling logic (how the model arrives to it's conclusion via algorithm or otherwise) from the platform code as a populate requirement so I can simplify maintenance of both the platform and the models. | New |  | Not started
BCDSS | 5.2.5 Need to clarify where store results and for how long - See previous TDB | As Populate Requirement I want to Automatically store execution results So I can Provide feedback to modeler | BCDSS-28 | As a backend user, I want to automatically store execution results and populate them back to the modeler as a requirement to provide feedback. | New |  | Not started
BCDSS | 5.2.1 | As Populate Requirement I want to Automatically update model repository with target predictive model upon acceptance based on conformance verification What is conformance verification So I can make available new or updated models for application | BCDSS-27 | As a backend user, I want to install automatic updating capability within the predictive model repository upon user acceptance of the information being offered so I can make new models available for application. | New |  | Not started
BCDSS | 5.2.7 | As Fetch (what are we fetching data models?Requirement We should map the requirements to a diagram depicting the business and technical flows I want to Auto-generate output So I can specify status if model inject ?ingest? | BCDSS-26 | As a user, I want to auto-generate output so I can specify status of model. | Deleted |  | Not started
BCDSS | 5.2.3 | As Fetch Requirement I want to Filter well formed claims (ambiguous. What are well formed claims ) for rating So I can Select target claim data for conformance | BCDSS-25 | As a user, I want to filter claims for ratings as a fetch requirement zo I can select target claim data for conformance . | Deleted |  | Not started
BCDSS | 5.2.6 | As Fetch Requirement I want to UI control So I can select target claim data set | BCDSS-24 | As a backend user, I want to select a target claim data set so I can evaluate it. | New |  | Not started
BCDSS | 5.2.7 | As Fetch Requirement I want to Automatically generate output So I can specify status of model inject ?ingest? | BCDSS-23 | As a user, I want the models to automatically generate output as a fetch requirement so I can specify status of model ingest | Deleted |  | Not started
BCDSS | 5.2.5 | As Fetch Requirement I want to Automatically evaluate So I can Ensure conformance to standards prior to injest | BCDSS-22 | As a user, I want the models to automatically evaluate ratings so I have conformance to model specifications What is this? | New (Revised) |  | Not started
BCDSS | 5.2.6 | As Fetch Requirement I want to UI Control So I can Select predictive model for inject | BCDSS-21 | As a user, I want to select predictive models for ingest, to rate claims | New |  | Not started
BCDSS | 5.2.5 | As Knee related disability I want to correlate predictive characteristics specified within the model, to issue specific characteristics within the target claims data So I can derive future disability ratings for the target knee issue | BCDSS-20 | As a model agent, I want to correlate predictive characteristics of knee disabilities within the model to pin point certain symptoms that could potentially increase or cause future disability ratings for the target knee issue. | New |  | Not started
BCDSS | 5.2.5 | As Knee related disability I want to Apply models So I can Determine whether the model is applicable to the target claims data | BCDSS-19 | As a model agent, I want to apply models to claims due to knee disabilities to determine whether the model is applicable to target the claim's date. Are we applying to original claims? I though only requests for increase at this point | New (Revised) |  | Not started
BCDSS | 5.2.1 | As Knee related disability I want to Identify predictive characteristics of knee related issues in original claims. So I can Forecast future requests for knee related rating increases. | BCDSS-18 | As a model agent, I want to identify predictive characteristics of knee related disabilities in claim. So I can forecast future requests for rating increases due to knee injury symptoms | New |  | Not started
BCDSS | 5.2.5 | As Ear related disability I want to correlate predictive characteristics specified within the model, to issue specific characteristics within the target claims data So I can derive future disability ratings for the target hearing loss issue | BCDSS-17 | As a model agent, I want to correlate predictive characteristics of ear disabilities within the model to pin point certain symptoms that could potentially increase or cause future disability ratings for the target hearing loss issue. | New |  | Not started
BCDSS | 5.2.5 | As Ear related disability I want to Apply models So I can Determine whether the model is applicable to the target claims date | BCDSS-16 | As a model agent, I want to apply models to claims due to Ear disabilities to determine whether the model is applicable to target the claim's date. | New (Revised) |  | Not started
BCDSS | 5.2.1 | As Ear related disability I want to Identify predictive characteristics of hearing loss related issues in original claims. So I can Forecast future requests for hearing loss related rating increases. | BCDSS-15 | As a model agent, I want to identify predictive characteristics of hearing loss related issues in original claims so I can forecast future requests for hearing loss rate increases due to ear related disabilities. | New |  | Not started
BCDSS | 5.2.2 | As Platform I want to Offer menu choices So I can inject selected claims data target, run against selected model and output result in selected outcome format | BCDSS-14 | As a user I want menu choices in the UI so I can control the selected claim's target data, the model to run the data against , and the output format. | New |  | Not started
BCDSS | 5.2.1 | As Platform I want to Provide a percentage of ratings accuracy So I can Show depiction of historical verse newly generated | BCDSS-13 | As a backend user, I want to develop a platform that can show the percentage of accuracy on the diagnosis the model predicted to show newly generated codes can be equally as precise as the codes diagnosed historically. | New |  | Not started
BCDSS | 5.2.7 C and E don’t seem to be saying the same thing re new and special cases | As Platform I want to Generate results depicting what met original rating and what did not So I can Generate an Exceptions List an outcome | BCDSS-12 | As a backend user, I want to develop a platform that can separate the original ratings from the new or special cases ratings so we have access to an exceptions list if we have a patient that does not fall under the general diagnosis for their aliment. | Deleted |  | Not started
BCDSS | 5.2.5 | As Platform I want to Run an analysis of original ratings versus newly generated rating on selected Target Claims Data So I can | BCDSS-11 | As a backend user, I want a platform to run analysis of original and new ratings on a selected Target Claims so I can compare the accuracy of data the platform produces. | New |  | Not started
BCDSS | 5.2.1 | As Operation Environment I want to Operate inside FTL-GC So I can Demonstrate | BCDSS-10 | As a backend user, I want an operation environment where I can demonstrate and put into action the diagnostic codes the model provided inside the FTL-GC | New |  | Not started
BCDSS | 5.2 | As Operation Environment I want to Operate inside FTL-GC So I can Test | BCDSS-9 | As a backend user, I want an operation environment where I can test codes inside FTL-GC to see if diagnostics will benefit the patient more or less. | New |  | Not started
BCDSS | 5.2 | As Operation Environment I want to Operate inside FTL-GC So I can Develop | BCDSS-8 | As a backend user, I want an operation environment where I can develop a model to produce diagnostic codes inside FTL-GC to better assist the customer. | New |  | Not started
BCDSS | 5.2.5 | As Repository I want to Analysis Data Set So I can Store generated results for evaluation | BCDSS-7 | As a backend user, I want analyzed data sets that I can store in a platform that will generate results for evaluation for a faster diagnostic. | New |  | Not started
BCDSS | 5.2.2 Need to answer question of where store and for how long - TBD | As Repository I want to Target Data Set So I can Store target claims data | BCDSS-6 | As a backend user, I want a repository for targets sets of data, so I can save new and old claims for improved predictions. | New |  | Not started
BCDSS | 5.2.4 | As Repository I want to Model Data Set So I can Store defined predictive models | BCDSS-5 | As a backend user, I want a storage place for model data so I can control predictive models. | New |  | Not started
BCDSS | 5.2.7 C and E are two different but equally important req. One auto reports and c: where do I want to view or retrieve that report | As Platform I want to Report Generator So I can Manage output content, format and target location | BCDSS-4 | As a manager, I want automatic reports, so I can see the effectiveness of programs. (Note; This does not seem to match the old so I can, investigate actual requirements) | Deleted |  | Not started
BCDSS | 5.2.5 | As Platform I want to Model Engine So I can Automate model application and rating derivation | BCDSS-3 | As a backend user, I want a place to upload models so the program can use them to automate ratings | New |  | Not started
BCDSS | 5.2 | As Platform I want to User Interface So I can Enable platform operation control | BCDSS-2 | As an administrator I want a user interface for platform operation control so I can do my job functions. | New |  | Not started
Note on E15: Department of Veterans Affairs: what means 'maintain'
Note on E20: Department of Veterans Affairs: what is directory data
Note on E33: Department of Veterans Affairs: Need to define 'backend users" Does not appear in BCDS roles