## Slide 1: Sprint 13 Review & Sprint 14 Planning
October 31st 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Samantha Hamilton | *
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | *
Comp Services | Paul J Shute | *
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | 
Office of Strategic Planning | Sarah Wear | *
OBPI Representative | Ellen Rosen (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Ganesh Panneer | *
PWS (BCDSS) | David Teague | 

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 13)
Objectives | Value Delivered
Regenerate Hibernate components for the database updates – identified while data load. Develop Knee ratings calculation Continue to gather reporting requirements. | Completed the regeneration of Hibernate components for the Modeling engine Completed DDM Data load Completed Knee aggregate contention and decision components Completed Knee rating calculations and it’s matching components in Java Found couple of issues in code review session – which will be addressed in Sprint 14
Requirements Updates Gathering Reporting requirements | Gathered information requested by SMEs as part of the action item from the BCDSS Analyst’s call. Shared it with the business and SMEs Working with Elizabeth on the gathered information in preparation for the deep dive sessions on Reports analysis
FTL Deployment | Deployed Sprint 12 & 13 code updates to Development and Test environments

## Slide 5: Challenges
Database connectivity issue
  Resolution
    Restarted the Oracle – Service which fixed the connectivity issue

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15 | BCDSS Sprint 16 | BCDSS Sprint 17
Commited | 8 | 22 | 25 | 21 | 16 | 0 | 0 | 0 | 0
Completed | 23 | 19 | 17 | 20 | 16 | 0 | 0 | 0 | 0

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 4 | 34 | 0

## Slide 8: BCDSS – Progress Update
Chart: 
| Administrator Requirement | Alerts | BCDS System | Dashboard | Manage Model | Modeling Engine | Orchestrate Model | Platform Requirement | Predictive Model Result
Resolved | 6 | 3 | 1 | 11 | 2
Open | 1 | 1 | 1 | 6 | 1 | 11 | 1 | 3 | 2
In Progress | 2

## Slide 9: Sprint 13 Retrospective
What went well?
Effective Time Utilization during the stand-up meetings was an improvement
Streamlined the Internal Document Review process
Reporting Meeting went well
What can Improve?
Continue to Communicate better during the internal team meetings
Realistic Effort estimation
Instant document updates, rather doing all at once. (Example: RTM, Developer Guide & SDD)

## Slide 10: Program Calendar
Sprint 13
(10/17 - 10/28)
10/28
Sprint 15
Completion
Sprint 14
Completion
Sprint 13
Completion
Legend
Completed Not Completed Future
11/11
Collaborative Deliverable
Package and VASIC 7
11/25
12/02
Sprint 16
Completion
12/16
Sprint 17
Completion
Collaborative Deliverable
Package and VASIC 6
Sprint 14
(10/31 – 11/11)
Sprint 15
(11/14 - 11/25)
Sprint 16
(11/28 - 12/02)
10/21
Sprint 17
(12/05 - 12/16)

## Slide 11: Sprint Forward (Sprint 14)
Develop Modeling Engine components
  To Implement getCurrent Ratings operation
  To Implement getDDM Data operation
  To Implement Edit Model operation
  To fix the Knee rating calculation issues found during code review / testing
Dashboard Enhancements
  To Implement Advanced Search for claims
Application Enhancements
  Enhance navigation menus for the entire application

## Slide 12: Questions
?

## Slide 13
Thank you!