## Slide 1: Sprint 21 Review & Sprint 22 Planning
February 24, 2017

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Jason Prewitt | *
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula /Montrica Hoover | *
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | 
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Ellen Rosen (Evoke) | *
Office of Strategic Planning | Jessica Eberhardt | *
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
PWC (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Ganesh Panneer | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward
Demonstration

## Slide 4: Objectives - Value Delivered (Sprint 21)
Objectives | Value Delivered
To get started on BCDSS v4.0 release Aggregate Reports Exception Handling – for all the various negative scenarios Implementation of Modeling Engine Operations getDDM Data Operation getCurrent Ratings Operation To complete Ear data validations and calculations for all the scenarios To enhance Knee calculations on the bilateral | Test URL – Is up and running in parallel with Development URL Working with Operations to enable the accessibility of BCDSS URL from VA Network Completed the Aggregate Reports Completed the Exception handling for Claim processing Completed the backend table changes for the Bulk processing Resolved 14 UI/UX defects
Requirements Updates | No new requirements
FTL Deployment | Deployed Sprint 21 code updates to Development & Test environment

## Slide 5: Challenges

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 16 | BCDSS Sprint 17 | BCDSS Sprint 18 | BCDSS Sprint 19 | BCDSS Sprint 20 | BCDSS Sprint 21 | BCDSS Sprint 22
Commited | 0 | 55 | 34 | 53 | 40 | 24
Completed | 17 | 42 | 17 | 40 | 35 | 32

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | Modeling Engine | Reopened
Number of Issues | 0 | 2 | 36 | 0

## Slide 8: BCDSS v4.0 Release Progress
Chart: 
| Administrator Requirement | Analysis Report | BCDS System | Bulk Processing | Exception Handling | Manage Model | Modeling Engine | Platform Requirement | Predictive Model | UI Requirement
Resolved | 2 | 32 | 2 | 1 | 1 | 1 | 1
Open | 1 | 2 | 2 | 4
In Progress | 2 | 1

## Slide 9: Sprint 21 Retrospective
What went well?
Exception Handling - both in the service and BCDSS web application
Team Dynamics improved as we progressed
What can Improve?
Knee Document – status?

## Slide 10: Program Calendar
Sprint 19
(01/09 - 01/20)
01/20
Sprint 21
Completion
Sprint 20
Completion
Sprint 19
Completion
Legend
Completed Not Completed Future
02/03
Collaborative Deliverable
Package and VASIC 10
02/17
03/03
Sprint 22
Completion
03/17
Sprint 23
Completion
Collaborative Deliverable
Package and VASIC 9
Sprint 20
(01/23 - 02/03)
Sprint 21
(02/06 - 02/17)
Sprint 22
(02/20 - 03/03)
Sprint 23
(03/06 - 03/17)
01/27
02/24

## Slide 11: Sprint Forward (Sprint 22)
Modeling Engine components
  Implementation of Modeling Engine Operations
    getDDM Data Operation
    getCurrent Ratings Operation
  To complete Ear data validations and calculations for all the scenarios
  To enhance Knee calculations on the bilateral
Application Enhancements
  Continue to make progress for BCDSS v4.0
  Bulk processing functionality
  Deployment of Web application and web services – in FTL

## Slide 12: Demonstration
Aggregate Reports
Exception Handling - across the application

## Slide 13: Questions
?

## Slide 14
Thank you!