## Slide 1: Sprint 20 Review & Sprint 21 Planning
February 24, 2017

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Jason Prewitt | *
Product Owner | Elizabeth Wollin | 
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula /Montrica Hoover | *
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | *
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Ellen Rosen (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
PWC (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Ganesh Panneer | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward
Demonstration

## Slide 4: Objectives - Value Delivered (Sprint 20)
Objectives | Value Delivered
To get started on BCDSS v4.0 release Detailed and Aggregate Reports Bulk processing functionality Implementation of Modeling Engine Operations To complete Ear data validations and calculations for all the scenarios To enhance Knee calculations on the bilateral Exception Handling – for all the various negative scenarios | Data load – and processing of new data refresh – in progress Completed the Detailed Reports Completed the UI/Business requirements on the Bulk processing webpage Completed the Implementation of Modeling Engine Edit Model Operation as a service. Resolved 13 UI/UX defects
Requirements Updates | No new requirements
FTL Deployment | Deployed Sprint 20 code updates to Development environment

## Slide 5: Challenges
Test URL - facing some challenges in having both Dev and Test URLs up and running simultaneously

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 16 | BCDSS Sprint 17 | BCDSS Sprint 18 | BCDSS Sprint 19 | BCDSS Sprint 20 | BCDSS Sprint 21 | BCDSS Sprint 22
Commited | 0 | 55 | 34 | 53 | 40
Completed | 17 | 42 | 17 | 40 | 35

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | Modeling Engine | Reopened
Number of Issues | 0 | 4 | 25 | 0

## Slide 8: Sprint 20 Retrospective
What went well?
Continuation of Effective distribution of work items throughout the sprint
What can Improve?
Exception Handling - both in the service and BCDSS web application

## Slide 9: Program Calendar
Sprint 19
(01/09 - 01/20)
01/20
Sprint 21
Completion
Sprint 20
Completion
Sprint 19
Completion
Legend
Completed Not Completed Future
02/03
Collaborative Deliverable
Package and VASIC 10
02/17
03/03
Sprint 22
Completion
03/17
Sprint 23
Completion
Collaborative Deliverable
Package and VASIC 9
Sprint 20
(01/23 - 02/03)
Sprint 21
(02/06 - 02/17)
Sprint 22
(02/20 - 03/03)
Sprint 23
(03/06 - 03/17)
01/27
02/24

## Slide 10: Sprint Forward (Sprint 21)
Develop Modeling Engine components
  Implementation of Modeling Engine Operations
    getDDM Data Operation
    getCurrent Ratings Operation
  To complete Ear data validations and calculations for all the scenarios
  To enhance Knee calculations on the bilateral
Application Enhancements
  Continue to make progress for BCDSS v4.0
  Detailed and Aggregate Reports
  Bulk processing functionality
  Exception Handling – for all the various negative scenarios
  Deployment of Web application and web services – in FTL

## Slide 11: Demonstration
Detailed Reports
Bulk Processing – Claims (Just the UI)

## Slide 12: Questions
?

## Slide 13
Thank you!