## Slide 1: Sprint 22 Review & Sprint 23 Planning
March 20, 2017

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Jason Prewitt | *
Product Owner | Elizabeth Wollin | 
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Montrica Hoover | *
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | *
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Kellen Ecker (Evoke) | *
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
PWC (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Ganesh Panneer | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 22)
Objectives | Value Delivered
BCDSS v4.0 release To complete End to End - Exception handling, data validations and calculations for all the scenarios To enhance Knee calculations on the bilateral Implementation of Modeling Engine Operations getDDM Data Operation getCurrent Ratings Operation | Working with Operations to enable the accessibility of BCDSS URL from VA Network End to End - Exception handling for Claim processing Scenario 1 – Happy Path Scenario 2 – No Pattern match found – after claim processing Scenario 3 – No decision records; Claim count with no corresponding diagnostics code in decision table Scenario 4 – All other system exceptions based on the numerical calculations Identified the Error Code & Description for all the valid exceptions Updated and delivered Collaborative Development Package, SDD and CPMP for the month of February 2017 Resolved 2 UI/UX defects
Requirements Updates | No new requirements
FTL Deployment | Deployed Sprint 22 code updates to Development environment

## Slide 5: Challenges
Accessibility of BCDSS URL

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 16 | BCDSS Sprint 17 | BCDSS Sprint 18 | BCDSS Sprint 19 | BCDSS Sprint 20 | BCDSS Sprint 21 | BCDSS Sprint 22
Commited | 0 | 55 | 34 | 53 | 40 | 24 | 21
Completed | 17 | 42 | 17 | 40 | 35 | 32 | 19

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 2 | 15 | 0

## Slide 8: BCDSS v4.0 Release Progress
Chart: 
| Administrator Requirement | Analysis Report | BCDS System | Bulk Processing | Exception Handling | Manage Model | Modeling Engine | Platform Requirement | Predictive Model | UI Requirement
Resolved | 2 | 40 | 2 | 1 | 1 | 1 | 1 | 1
Open | 1 | 3 | 2 | 3
In Progress | 2 | 1

## Slide 9: Sprint 22 Retrospective
What went well?
What can Improve?

## Slide 10: Program Calendar
Sprint 19
(01/09 - 01/20)
01/20
Sprint 21
Completion
Sprint 20
Completion
Sprint 19
Completion
Legend
Completed Not Completed Future
02/03
Collaborative Deliverable
Package and VASIC 10
02/17
03/03
Sprint 22
Completion
03/17
Sprint 23
Completion
Collaborative Deliverable
Package and VASIC 9
Sprint 20
(01/23 - 02/03)
Sprint 21
(02/06 - 02/17)
Sprint 22
(02/20 - 03/03)
Sprint 23
(03/06 - 03/17)
01/27
02/24

## Slide 11: Sprint Forward (Sprint 23)
Modeling Engine components
  Implementation of Modeling Engine Operations
    getDDM Data Operation
    getCurrent Ratings Operation
  To enhance Knee calculations on the bilateral
Application Enhancements
  Continue to make progress for BCDSS v4.0
  Bulk processing functionality
  Deployment of Web application and web services – in FTL

## Slide 12: Questions
?

## Slide 13
Thank you!