## Slide 1: Sprint 23 Review & Sprint 24 Planning
March 20, 2017

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Jason Prewitt | 
Product Owner | Elizabeth Wollin | 
Innovation Coordinator | Heath A Forney | *
OBPI Representative | Kaitlin Conron | 
Comp Services | Montrica Hoover | 
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | 
Office of Strategic Planning | Sarah Wear | *
OBPI Representative | Kellen Ecker (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
PWC (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Ganesh Panneer | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 22)
Objectives | Value Delivered
BCDSS v4.0 release Implementation of Modeling Engine Operations getDDM Data getCurrent Ratings To enhance Knee calculations on the bilateral | BCDSS URL now accessible from outside FTL (http://bcds.vaftl.us:8080/bcds-web/#/) Completed the Implementation of Modeling Engine operations getDDM Data getCurrent Ratings Completed Knee Model Decomposition Analysis Document Participated in the BCDSS Modeling Outcomes / Wrap up meeting
Requirements Updates | No new requirements
FTL Deployment | Deployed Sprint 23 code updates to Development environment

## Slide 5: Challenges
None

## Slide 6: Metrics – Velocity
Chart: Velocity Chart – based on Story points
| BCDSS Sprint 16 | BCDSS Sprint 17 | BCDSS Sprint 18 | BCDSS Sprint 19 | BCDSS Sprint 20 | BCDSS Sprint 21 | BCDSS Sprint 22 | BCDSS Sprint 23 | BCDSS Sprint 24
Commited | 0 | 55 | 34 | 53 | 40 | 24 | 21 | 22 | 17
Completed | 17 | 42 | 17 | 40 | 35 | 32 | 19 | 22 | 0
Overall
Team Velocity - 26

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 0 | 19 | 0

## Slide 8: BCDSS v4.0 Release Progress
Chart: 
| Analysis Report | BCDS System | Bulk Processing | Exception Handling | Manage Model | Modeling Engine | Platform Requirement | Predictive Model | UI Requirement
Resolved | 2 | 40 | 2 | 1 | 1 | 1 | 1 | 3 | 1
Open | 1
In Progress | 2

## Slide 9: Sprint 23 Retrospective
What went well?
Development phase on track
Improved documentation
Effective Team coordination
What can Improve?
To be proactive than reactive

## Slide 10: Program Calendar
Sprint 20
(01/23 - 02/03)
02/03
Sprint 22
Completion
Sprint 21
Completion
Sprint 20
Completion
Legend
Completed Not Completed Future
02/17
Collaborative Deliverable
Package and VASIC 10
03/03
03/17
Sprint 23
Completion
03/31
Sprint 24
Completion
Sprint 21
(02/06 - 02/17)
Sprint 22
(02/20 - 03/03)
Sprint 23
(03/06 - 03/17)
Sprint 24
(03/20 - 03/31)
02/24
Collaborative Deliverable
Package and VASIC 11
03/24

## Slide 11: Sprint Forward (Sprint 24)
Modeling Engine components
  To enhance Knee calculations on the bilateral
Application Enhancements
  Bulk processing functionality
  Deployment of Web application and web services – in FTL

## Slide 12: Questions
?

## Slide 13
Thank you!