## Slide 1: Sprint 9 Review & Sprint 10 Planning
September 6th 2016

## Slide 2: Attendance
Office SME |  | Name |  | Attendance
Veteran Health Administration Innovations Program |  |  |  | 
Innovation Coordinator | Heath A Forney |  | * | 
OSP Liaison | Sarah Wear |  |  | 
OBPI Representative | Casey Curry |  |  | 
Product Owner | Elizabeth Wollin |  | * | 
OBPI Representative | Kaitlin Conron |  |  | 
Comp Services | Matthew Padula |  | * | 
Comp Services | Paul J Shute |  |  | 
SME | VILAYPHONG SENTHEP |  | * | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh |  | * | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy |  | * | 
Pro Sphere (BCDSS) | Darrell Dorman |  | * | 
PWS (BCDSS) | David Teague |  |  | 
Pro Sphere (BCDSS) | Dominic Yeh |  | * | 
Pro Sphere (BCDSS) | Erik Rothwell |  |  | 
Pro Sphere (BCDSS) | Ganesh Panneer |  | * | 
Pro Sphere (BCDSS) | Jeffrey Bamba |  | * | 
Pro Sphere (BCDSS) | Masud Habib |  | * | 
Pro Sphere (BCDSS) | Rebecca Garcia DeJesus |  | * | 
Pro Sphere (BCDSS) | Vasudeva Rayapati |  | * | 

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 9)
Objectives | Value Delivered
Modeling Engine – Analysis and Design Admin Dashboard Updates Fix any UI/UX related defects in Rater and Modeling Agent Dashboards | Created Modeling Engine service WSDL and XSD Analyzed Distributed Data Model (DDM) tables for modeling engine. Implemented Sorting and Filtering options for all the dashboards Updates to Administrator Dashboard Edit User functionality Reset Password
Requirements Updates | Accept/Reject functionality Gathered requirements on the Accept / Reject functionality in claims processing Bulk Processing Created Mockups for the Bulk Claim processing and reviewed with SMEs
FTL Deployment | Deployed Sprint 9 code updates to Development and Test environments

## Slide 5: Challenges
Maintain business rhythm with only one developer

## Slide 6: Metrics – Velocity
Chart: Velocity Chart – based on Story points
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15 | BCDSS Sprint 16 | BCDSS Sprint 17
Commited | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 7: Metrics – Number of Tasks
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 4 | 34 | 0

## Slide 8: Sprint 9 Retrospective
What went well?
Getting some momentum on the direction
Were able to accomplish more than committed.
What can Improve?
Better document process to keep track the change in requirements.
Maintain a backlog of functional requirements for Pilot / Production phases
More formal meeting notes from the meetings and save them in GitHub

## Slide 9: Program Calendar
Sprint 6
(7/11 - 7/22)
7/22
8/19
Sprint 8
Completion
Sprint 7
Completion
Sprint 6
Completion
Legend
Completed Not Completed Future
8/5
Collaborative Deliverable
Package and VASIC 3
7/29
9/2
Sprint 9
Completion
9/16
Sprint 10
Completion
Collaborative Deliverable
Package and VASIC 4
Sprint 7
(7/25 - 8/5)
Sprint 8
(8/8 - 8/19)
Sprint 9
(8/22 - 9/2)
8/26
Sprint 10
(9/5 - 9/16)

## Slide 10: Sprint Forward (Sprint 10)
To conduct design review sessions for Modeling engine components (Framework and Utilities)
  Create Data base structure and tables
To Improve Dashboard functionalities
  Administrator Dashboard
    Add Users

## Slide 11: Questions
?

## Slide 12
Thank you!