## Slide 1: BCDSS Sprint 5 Review & Sprint 6 Planning Meeting
July 11 2016

## Slide 2: BCDSS – Sprint 5 Review & Sprint 6 Planning Attendance
Office SME |  | Name |  | Attendance
Veteran Health Administration Innovations Program |  |  |  | 
Innovation Coordinator | Heath A Forney |  | * | 
OSP Liaison | Edward L Wells |  |  | 
Product Owner | Elizabeth Wollin |  | * | 
OBPI Representative | Kaitlin Conron |  | * | 
Comp Services | Matthew Padula |  | * | 
Comp Services | Paul J Shute |  |  | 
SME | VILAYPHONG SENTHEP |  |  | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh |  | * | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy |  | * | 
Pro Sphere (BCDSS) | Darrell Dorman |  | * | 
PWS (BCDSS) | David Teague |  |  | 
Pro Sphere (BCDSS) | Dominic Yeh |  | * | 
Pro Sphere (BCDSS) | Erik Rothwell |  |  | 
Pro Sphere (BCDSS) | Ganesh Panneer |  | * | 
Pro Sphere (BCDSS) | Jeffrey Bamba |  | * | 
Pro Sphere (BCDSS) | Masud Habib |  |  | 
Pro Sphere (BCDSS) | Rebecca Garcia DeJesus |  | * | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | 

## Slide 3: BCDSS – Sprint 5 Review & Sprint 6 Planning Agenda
Objectives
Value Delivered
Challenges
Retrospective
Program Calendar
Sprint Forward

## Slide 4: BCDSS – Sprint 5 Review & Sprint 6 Planning Objectives - Value Delivered (Sprint 5)
Chart: 
Chart: 
Chart: 
Chart: 
Completed Liquibase updates in BCDSS Application
Completed DDM data load into the FTL database
Requirements for Model output / Results
  Requirements gathering sessions with the business team on Model output/Results for each contentions
  Created mockups of the Result’s page
Pending: mockups to be updated based on the discussions and get reviewed by business
Continue to work on Rater’s Dashboard for Implementing Search and Model selection functionalities.
Gather requirements around Running the Model against the Claims and it’s Results
Objectives
Value Delivered

## Slide 5: BCDSS – Sprint 5 Review & Sprint 6 Planning Challenges
Challenge
  Our schedule for Sprint 5 was impacted by the issue with Liquibase
Mitigation
  Developers were able to establish a workaround so the code could be deployable from GitHub
  Analyzed the reasoning behind the Liquibase issue and made schema changes to the data model

## Slide 6: BCDSS – Sprint 5 Review & Sprint 6 Planning Metrics – Velocity
Chart: Velocity Chart – based on Story points
| BCDSS Sprint 0 | BCDSS Sprint 1 | BCDSS Sprint 2 | BCDSS Sprint 3 | BCDSS Sprint 4 | BCDSS Sprint 5
Commited | 20 | 32 | 18 | 19 | 25 | 18
Completed | 12 | 14 | 19 | 12 | 16 | 18

## Slide 7: BCDSS – Sprint 5 Review & Sprint 6 Planning Metrics – Number of Tasks
Chart: Number of tasks
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 5 | 24 | 0

## Slide 8: BCDSS – Sprint 5 Review & Sprint 6 Planning Sprint 5 Retrospective
Chart: 
Chart: 
Chart: 
Chart: 
Communications between stakeholders
  More participation in mockups discussions
  Communications between development team members
Don’t wait until retrospective to voice suggestions/comments
Continuous feeding of “For Production Log”
Rapid response to issue with Liquibase and the reasons behind the issue will be documented for future releases
Constant Improvement in terms of communication between the stake holders
What Went Well
What Can Improve

## Slide 9: BCDSS – Sprint 5 Review & Sprint 6 Planning Program Calendar
Sprint 3
(5/30 - 6/10)
Sprint 5
(6/27 - 7/8)
Sprint 6
(7/11 - 7/22)
Sprint 4
(6/13 - 6/24)
5/27
6/24
Sprint 4
Completion
Sprint 3
Completion
Sprint 2
Completion
Legend
Completed Not Completed Future
6/10
Collaborative Deliverable
Package and VASIC 1
6/06
7/8
Sprint 5
Completion
7/22
Sprint 6
Completion
Collaborative Deliverable
Package and VASIC 2
Notes: Add brief notes about the Sprint deliverables in this section - Elizabeth

## Slide 10: BCDSS – Sprint 5 Review & Sprint 6 Planning Sprint Forward (Sprint 6)
Include Claim retrieval process in Rater Dashboard
Start work on the Modeling Agent Dashboard

## Slide 11: BCDSS – Sprint 5 Review & Sprint 6 Planning Questions
?

## Slide 12
Thank you!