## Slide 1: Sprint 14 Review & Sprint 15 Planning
November 14th 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Samantha Hamilton | *
Product Owner | Elizabeth Wollin | 
Innovation Coordinator | Heath A Forney | *
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | *
Comp Services | Paul J Shute | *
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | 
Office of Strategic Planning | Sarah Wear | *
OBPI Representative | Ellen Rosen (Evoke) | *
Office of Strategic Planning | Jessica Eberhardt | *
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Ganesh Panneer | *
PWS (BCDSS) | David Teague | 

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Demonstration
Progress Update
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 14)
Objectives | Value Delivered
Develop Modeling Engine components To Implement getCurrent Ratings operation To Implement getDDM Data operation To fix the Knee rating calculation issues found during code review / testing Dashboard Enhancements To Implement Advanced Search for claims Application Enhancements Enhance navigation menus for the entire application | Completed getDDM Ratings operation Identified few issues in getCurrent Ratings operation Expected to fix in Sprint 15 Dashboard Updates Implemented Advanced Search for claims Implemented Grid – pagination Application Enhancements Implemented navigation menu for other pages
Requirements Updates Reporting requirements | Finalized Reporting requirements with business. Team met internally to formalize the standards and the Implementation approach for Reporting Requirements
FTL Deployment | Deployed Sprint 14 code updates to Development and Test environments

## Slide 5: Challenges
FTL Deployment challenge
  Resolution
    Implemented a automated Build process

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15
Commited | 8 | 22 | 25 | 21 | 16 | 44 | 0
Completed | 23 | 19 | 17 | 20 | 16 | 34 | 0

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 4 | 32 | 0

## Slide 8: BCDSS – Progress Update
Chart: 
| Administrator Requirement | BCDS System | Dashboard | Manage Model | Modeling Engine | Orchestrate Model | Platform Requirement | Predictive Model Result
Resolved | 6 | 1 | 4 | 1 | 13 | 2
Open | 1 | 8 | 1 | 3 | 1
In Progress | 1 | 2

## Slide 9: Sprint 14 Retrospective
What went well?
Meeting with Dave and modeling team is really productive.
What can Improve?
Proper Unit testing

## Slide 10: Program Calendar
Sprint 13
(10/17 - 10/28)
10/28
Sprint 15
Completion
&
Release BCDSS v2.0
Sprint 14
Completion
Sprint 13
Completion
Legend
Completed Not Completed Future
11/11
Collaborative Deliverable
Package and VASIC 7
11/25
12/02
Sprint 16
Completion
12/16
Sprint 17
Completion
Collaborative Deliverable
Package and VASIC 6
Sprint 14
(10/31 – 11/11)
Sprint 15
(11/14 - 11/25)
Sprint 16
(11/28 - 12/02)
10/21
Sprint 17
(12/05 - 12/16)

## Slide 11: Sprint Forward (Sprint 15)
Develop Modeling Engine components
  Fix the getCurrent Ratings Operation
  Implement EAR model processing functionality.
  To complete the Integration between the BCDSS web-application & Modeling engine web service
  Display Processing Results
Application Enhancements
  Deployment of Web application and web services – in FTL
  Release BCDSS v2.0

## Slide 12: Questions
?

## Slide 13
Thank you!