## Slide 1: Sprint 16 Review & Sprint 17 Planning
December 12, 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Samantha Hamilton | 
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | *
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | *
Office of Strategic Planning | Sarah Wear | *
OBPI Representative | Ellen Rosen (Evoke) | *
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
PWS (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Ganesh Panneer | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 16)
Objectives | Value Delivered
Validate Knee Calculations Conduct Release & Sprint planning meetings for BCDSS v3.0 release Release BCDSS v2.0 to Test environment | Analyzed the dev instance of the claims database Made progress on the Knee calculations Partial results are now being populated in the Results page Conducted Release / Sprint planning for the next sprint – which includes Result page updates to include Agree/Disagree functionality Report page updates Implementing Ear model processing
Requirements Updates | 
FTL Deployment | Deployed Sprint 16 code updates to Development environment

## Slide 5: Challenges
Data Validation

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 16 | BCDSS Sprint 17 | BCDSS Sprint 18 | BCDSS Sprint 19 | BCDSS Sprint 20 | BCDSS Sprint 21 | BCDSS Sprint 22
Commited | 0
Completed | 17

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 1 | 14 | 0

## Slide 8: BCDSS – Progress Update
Chart: 
| Administrator Requirement | Alerts | Analysis Report | Functional Requirement | Manage Model | Modeling Engine | Platform Requirement | Predictive Model Result | UI Requirement
In Progress | 3 | 1 | 1
Open | 2 | 1 | 3 | 2 | 4 | 3 | 1 | 3 | 1

## Slide 9: Sprint 16 Retrospective
What went well?
Internal Use of Project Documentation
What can Improve?
Data Validation techniques in FTL and other environments

## Slide 10: Program Calendar
Sprint 16
(11/28 - 12/09)
12/09
Sprint 18
Completion
Sprint 17
Completion
Sprint 16
Completion
Legend
Completed Not Completed Future
12/23
Collaborative Deliverable
Package and VASIC 9
01/06
01/20
Sprint 19
Completion
02/03
Sprint 20
Completion
Collaborative Deliverable
Package and VASIC 8
Sprint 17
(12/12 - 12/23)
Sprint 18
(12/26 - 01/06)
Sprint 19
(01/09 - 01/20)
Sprint 20
(01/23 - 02/03)
12/30
01/27

## Slide 11: Sprint Forward (Sprint 17)
Develop Modeling Engine components
  To Complete the Data Validation and Calculation of Knee processing claims
  To implement EAR model processing functionality
  To implement Agree/Disagree functionality to the process flow
  To implement hyperlinks, pop-up and other mouse over user requirement on the Result page
  To promote the final BCDSS v2.0 into Test Environment
Application Enhancements
  Deployment of Web application and web services – in FTL

## Slide 12: Questions
?

## Slide 13
Thank you!