## Slide 1: Sprint 17 Review & Sprint 18 Planning
December 27, 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Jason Prewitt | *
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | 
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | 
SME | VILAYPHONG SENTHEP | *
Office of Strategic Planning | Sarah Wear | *
OBPI Representative | Ellen Rosen (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
PWS (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Ganesh Panneer | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward
Demonstration

## Slide 4: Objectives - Value Delivered (Sprint 17)
Objectives | Value Delivered
To Complete the Data Validation and Calculation of Knee processing claims To implement Agree/Disagree functionality to the process flow To implement hyperlinks, pop-up and other mouse over user requirement on the Result page To promote the final BCDSS v2.0 into Test Environment | Analyzed the dev instance of the claims database Completed Knee data validations and calculations Identified a data issue for the bilateral indicators Results page is now populating all the values from a claim processing Started working on the Result page updates To include Agree/Disagree checkbox To include Hyperlinks for more details Promoted BCDSS v2.0 into Test Environment
Requirements Updates | No new requirements
FTL Deployment | Deployed Sprint 17 code updates to Development environment Deployed BCDSS v2.0 into Test Environment

## Slide 5: Challenges

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 16 | BCDSS Sprint 17 | BCDSS Sprint 18 | BCDSS Sprint 19 | BCDSS Sprint 20 | BCDSS Sprint 21 | BCDSS Sprint 22
Commited | 0 | 55
Completed | 17 | 42

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 5 | 33 | 0

## Slide 8: BCDSS – Progress Update
Chart: 
| Administrator Requirement | Alerts | Analysis Report | Dashboard | Manage Model | Model Agent Requirement | Modeling Engine | Platform Requirement | Predictive Model Result | UI Requirement
Resolved | 1 | 1 | 2
Open | 1 | 1 | 3 | 4 | 2 | 5 | 1 | 1 | 1
In Progress | 2

## Slide 9: Sprint 16 Retrospective
What went well?
Were able to complete the data validations for Knee
As part of Lesson Learnt – we documented the entire Knee calculations step by step - which can be utilized as a reference document for future use
Full utilization of team meetings
What can Improve?
To get better at our estimation skills

## Slide 10: Program Calendar
Sprint 16
(11/28 - 12/09)
12/09
Sprint 18
Completion
Sprint 17
Completion
Sprint 16
Completion
Legend
Completed Not Completed Future
12/23
Collaborative Deliverable
Package and VASIC 9
01/06
01/20
Sprint 19
Completion
02/03
Sprint 20
Completion
Collaborative Deliverable
Package and VASIC 8
Sprint 17
(12/12 - 12/23)
Sprint 18
(12/26 - 01/06)
Sprint 19
(01/09 - 01/20)
Sprint 20
(01/23 - 02/03)
12/30
01/27

## Slide 11: Sprint Forward (Sprint 18)
Develop Modeling Engine components
  Code enhancements for Knee calculations on the bilateral
  Develop Ear Ratings calculations
  Develop Modeling Engine Services for Ear Contentions and Decisions
  Ability for the Rater/Modeling Agent to choose Agree/Disagree and “Save” – claim processing results
  Fix some minor UI / UX defects related to Dashboard
Application Enhancements
  Deployment of Web application and web services – in FTL

## Slide 12: Demonstration
Claim processing Results
  Results are now being populated in Results page
Advanced Search – Filter
  By Regional Office
  By Contention

## Slide 13: Questions
?

## Slide 14
Thank you!