## Slide 1: Sprint 15 Review & Sprint 16 Planning
November 28th 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Samantha Hamilton | *
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | *
Comp Services | Paul J Shute | 
OBPI Representative | Sasha Gillian | *
SME | VILAYPHONG SENTHEP | 
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Ellen Rosen (Evoke) | 
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Erik Rothwell | 
Pro Sphere (BCDSS) | Vasudeva Rayapati | *
Pro Sphere (BCDSS) | Ganesh Panneer | *
PWS (BCDSS) | David Teague | 

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Progress Update
Retrospective
Program Calendar
Sprint Forward
Demonstration

## Slide 4: Objectives - Value Delivered (Sprint 15)
Objectives | Value Delivered
Develop Modeling Engine components Fix the getCurrent Ratings Operation To complete the Integration between the BCDSS web-application & Modeling engine web service Display Processing Results Application Enhancements Deployment of Web application and web services – in FTL Release BCDSS v2.0 | Completed getCurrent Ratings operation Completed the Integration between the BCDSS web-application & Modeling engine web service Successfully deployed BCDSS v2.0 in FTL Dashboard Updates Display processing Results
Requirements Updates | 
FTL Deployment | Deployed Sprint 15 code updates to Development and Test environments

## Slide 5: Challenges

## Slide 6: Metrics – Velocity
Chart: 
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15
Commited | 8 | 22 | 25 | 21 | 16 | 44 | 37
Completed | 23 | 19 | 17 | 20 | 16 | 34 | 36

## Slide 7: Metrics – Number of Tasks
Chart: 
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 4 | 32 | 0

## Slide 8: BCDSS – Progress Update
Chart: 
| Administrator Requirement | BCDS System | Dashboard | Manage Model | Modeling Engine | Platform Requirement | Predictive Model Result
Resolved | 3 | 1 | 5 | 1 | 20 | 2 | 1

## Slide 9: Sprint 15 Retrospective
What went well?
BCDSS v2.0 Release
Even though, Development team had their share of issues in terms of coordination/communication – everyone was focused to deliver on time.
Automated Build – process along with Success/Failure email notification
Team Dynamics – getting better
What can Improve?
Better Design review sessions among the team members – so that everyone is on the same page from the get go.
Better use of JIRA/Confluence for knowledge sharing
Better use of internal meetings for clarifying both technical & business requirements
Better use of GitHub – configuration techniques.

## Slide 10: Program Calendar
Sprint 13
(10/17 - 10/28)
10/28
Sprint 15
Completion
&
Release BCDSS v2.0
Sprint 14
Completion
Sprint 13
Completion
Legend
Completed Not Completed Future
11/11
Collaborative Deliverable
Package and VASIC 7
11/25
12/09
Sprint 16
Completion
12/23
Sprint 17
Completion
Collaborative Deliverable
Package and VASIC 6
Sprint 14
(10/31 – 11/11)
Sprint 15
(11/14 - 11/25)
Sprint 16
(11/28 - 12/09)
10/21
Sprint 17
(12/12 - 12/23)

## Slide 11: Sprint Forward (Sprint 16)
Develop Modeling Engine components
  To implement EAR model processing functionality
  To have a clean subset of data in FTL – to complete the claim processes
  Final - Release Deployment of BCDSS v2.0
Application Enhancements
  Deployment of Web application and web services – in FTL

## Slide 12: Demonstration
BCDSS – v2.0 Release Demo

## Slide 13: Questions
?

## Slide 14
Thank you!