## Slide 1: BCDSS Sprint 2 Review & Sprint 3 Planning Meeting
May 31, 2016

## Slide 2: BCDSS – Sprint 2 Review & Sprint 3 Planning Attendance
Office SME |  | Name |  | Attendance
Veteran Health Administration Innovations Program |  |  |  | 
Innovation Coordinator | Brian Stevenson |  | * | 
Innovation Coordinator | Heath A Forney |  | * | 
OSP Liaison | Edward L Wells |  |  | 
Product Owner | Elizabeth Wollin |  | * | 
OBPI Representative | Kaitlin Conron |  |  | 
OBPI Representative | Matthew Padula |  | * | 
SME | Paul J Shute |  |  | 
SME | VILAYPHONG SENTHEP |  |  | 
OBPI Representative | Karla Leal |  |  | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh |  | * | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy |  | * | 
Pro Sphere (BCDSS) | Darrell Dorman |  | * | 
PWS (BCDSS) | David Teague |  |  | 
Pro Sphere (BCDSS) | Dominic Yeh |  |  | 
Pro Sphere (BCDSS) | Erik Rothwell |  | * | 
Pro Sphere (BCDSS) | Ganesh Panneer |  | * | 
Pro Sphere (BCDSS) | Jeffrey Bamba |  | * | 
Pro Sphere (BCDSS) | Rebecca Garcia DeJesus |  |  | 
Pro Sphere (BCDSS) | Vasudeva Rayapati |  | * | 

## Slide 3: BCDSS – Sprint 2 Review & Sprint 3 Planning Agenda
Objectives
Value Delivered
Challenges
Demonstration
Retrospective
Program Calendar
Sprint Forward

## Slide 4: BCDSS – Sprint 2 Review & Sprint 3 Planning Objectives (Sprint 2)
Implement Logon/Logoff process
Create Oracle schemas for the Distributed Data Models (DDMs)
Create Logical and Physical data models for the DDMs
Generate and receive approval for Administrator Dashboard and resulting UI/UX elements
Update all documentation for the Collaborative Deliverable Package

## Slide 5: BCDSS – Sprint 2 Review & Sprint 3 Planning Value Delivered
Wrapped up wireframes for
  Login authentication
  Rater Dashboard &
    Work Queue option
    Select Model option &
    Advanced Search criteria options proposed to business – awaiting approval
Created UI templates for login process
Completed the Logical & Physical data model for the Distributed Data Models (DDMs)
Created Database objects in the DEV schema in support of the DDM
Refinements to Ear and Knee models – based on data verification, modified scripts for re-run
Defined Continuous Integration process
Created various documents for the Collaborative Deliverable Package

## Slide 6: BCDSS – Sprint 2 Review & Sprint 3 Planning Challenges
Challenge
  There was a limit to number of concurrent remote connections to our BCDS sandbox environment within the FTL
Mitigation
  Put in a support ticket to up the number of allowable connections

## Slide 7: BCDSS – Sprint 2 Review & Sprint 3 Planning Demonstration

## Slide 8: BCDSS – Sprint 2 Review & Sprint 3 Planning Metrics – Velocity
Chart: Velocity Chart
| BCDSS Sprint 0 | BCDSS Sprint 1 | BCDSS Sprint 2 | BCDSS Sprint 3 | BCDSS Sprint 4
Commited | 20 | 32 | 18 | 0 | 0
Completed | 12 | 14 | 19 | 0 | 0

## Slide 9: BCDSS – Sprint 2 Review & Sprint 3 Planning Metrics – Number of Tasks
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 3 | 20 | 0

## Slide 10: BCDSS – Sprint 2 Review & Sprint 3 Planning Sprint 1 Retrospective
Chart: 
Chart: 
Chart: 
Chart: 
Updating tasks in JIRA promptly
Metrics for upper management communication
Collaboration between team members demonstrated the required integration is in place
Processes for Release Management were identified
Recurrent communications with the government facilitated the detection of important information
Things are moving in the right direction
What Went Well
What Can Improve

## Slide 11: BCDSS – Sprint 2 Review & Sprint 3 Planning Sprint 2 Retrospective
Chart: 
Chart: 
Chart: 
Chart: 
Single point failure – need back ups for Development roles
Fix Wi-Fi issues and plan to use VA Lync meetings
Things are going well, as per the plan
What Went Well
What Can Improve

## Slide 12: BCDSS – Sprint 2 Review & Sprint 3 Planning Program Calendar
Sprint 0
(4/18 - 4/29)
Sprint 2
(5/16 - 5/27)
Sprint 3
(5/30 - 6/10)
Sprint 1
(5/02 - 5/13)
5/13
5/27
4/29
6/24
Sprint 4
Completion
Sprint 3
Completion
Sprint 2
Completion
Sprint 0
Completion
Legend
Completed Not Completed Future
6/10
Sprint 1
Completion
Collaborative Deliverable
Package and VASIC 1
6/03
SDD, RTM
Ear & Knee Models
Database Structure & Wireframes
Notes: Add brief notes about the Sprint deliverables in this section - Elizabeth

## Slide 13: BCDSS – Sprint 2 Review & Sprint 3 Planning Sprint Forward (Sprint 3)
Prioritization of User management process tasks
Prioritization of Role-based security tasks
Continue to do wireframe updates for Modeling Agent and Administrative Dashboard
Wrap up Logon/Logoff process
Start work on the Dashboard for Rater

## Slide 14: BCDSS – Sprint 2 Review & Sprint 3 Planning Questions
?

## Slide 15
Thank you!