## Slide 1
BCDSS Weekly Status Report
PM: Rebecca Garcia De Jesus
ACCOMPLISHMENTS
Continued discussions of mockups of the Results page
Conducted Status Meeting, SME Meeting, Code Peer Review
Developed Raters Dashboard
Finished Sprint 5
NEXT STEPS
Sprint 6
Continue updating models
Adjust work based on contract mod
ISSUES
Onboarding
  Masud Habib received the PIV Card;
VA Sensitive Information Configuration File (possible replacement for other work)
  Tom Murphy approved expanding models to be based on diagnostic codes
Issue with Liquibase causing code to be un-deployable. Workaround stablished in order to have the code ready in Github. Developer working on final fix. ETC: July 10th.
RISKS
If new data is required to be added to the models then a new table structure and matrix data will need to be developed. Low. Status: Pending.
If the expansion of the scope requires a significant amount of manpower, then the schedule will require accommodations for these changes.