## Slide 1: Sprint 10 Review & Sprint 11 Planning
September 19th 2016

## Slide 2: Attendance
Office SME | Name | Attendance
Veteran Health Administration Innovations Program |  | 
OBPI Representative | Casey Curry | 
Product Owner | Elizabeth Wollin | *
Innovation Coordinator | Heath A Forney | 
OBPI Representative | Kaitlin Conron | 
Comp Services | Matthew Padula | *
Comp Services | Paul J Shute | *
OSP Liaison | Sarah Wear | 
OBPI Representative | Sasha Gillian | *
SME | VILAYPHONG SENTHEP | *
Office of Strategic Planning | Sarah Wear | 
OBPI Representative | Ellen Rosen (Evoke) | *
Office of Strategic Planning | Jessica Eberhardt | 
Pro Sphere (BCDSS) | Bhupinder Pal. Singh | 
Pro Sphere (BCDSS) | Chiranjeevi Puttaswamy | *
Pro Sphere (BCDSS) | Darrell Dorman | *
PWS (BCDSS) | David Teague | 
Pro Sphere (BCDSS) | Dominic Yeh | *
Pro Sphere (BCDSS) | Erik Rothwell | *
Pro Sphere (BCDSS) | Ganesh Panneer | *
Pro Sphere (BCDSS) | Jeffrey Bamba | 
Pro Sphere (BCDSS) | Masud Habib | *
Pro Sphere (BCDSS) | Vasudeva Rayapati | *

## Slide 3: Agenda
Objectives
Value Delivered
Challenges
Demonstration
Retrospective
Program Calendar
Sprint Forward

## Slide 4: Objectives - Value Delivered (Sprint 10)
Objectives | Value Delivered
To conduct design review sessions for Modeling engine components (Framework and Utilities) Create Data base structure and tables Identify components, frameworks required for modeling engine. Analyze and document rating calculations for Knee and Ear models. To Improve Dashboard functionalities Administrator Dashboard Add Users | Analyzed Distributed Data Model (DDM) tables for modeling engine. Designed and analyzed modeling engine process flow, components and utilities. Updates to Administrator Dashboard Ability to Add user Edit User Reset Password
Requirements Updates | Accept/Reject functionality Created a Change Request Analysis report on the Accept / Reject functionality along with Process flow Use cases Assumptions and Questions
FTL Deployment | Deployed Sprint 10 code updates to Development and Test environments

## Slide 5: Challenges
No Challenges

## Slide 6: Demonstration
Demonstration of Administrator Dashboard
  Edit User
  Reset Password
  Create New User
Demonstration of Rater/Modeling Agent Dashboard
  Using Filter
  Sorting

## Slide 7: Metrics – Velocity
Chart: Velocity Chart – based on Story points
| BCDSS Sprint 9 | BCDSS Sprint 10 | BCDSS Sprint 11 | BCDSS Sprint 12 | BCDSS Sprint 13 | BCDSS Sprint 14 | BCDSS Sprint 15 | BCDSS Sprint 16 | BCDSS Sprint 17
Commited | 8 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 8: Metrics – Number of Tasks
Chart: 
| Open | Closed | Resolved | In Progress | Reopened
Number of Issues | 0 | 1 | 25 | 0

## Slide 9: Sprint 10 Retrospective
What went well?
Good communication between the team
Immediate bug fixes for the issues reported in the current sprint
Quality time spent on the code and document reviews
Good interactive meetings for Accept/Reject functionality; Would like to see the same kind of Interactive requirement gathering meetings in future;
What can Improve?
Periodic Review of Sprint Backlog – with team to get updates on the user story prioritization

## Slide 10: Program Calendar
Sprint 10
(9/5 - 9/16)
9/16
10/14
Sprint 12
Completion
Sprint 11
Completion
Sprint 10
Completion
Legend
Completed Not Completed Future
9/30
Collaborative Deliverable
Package and VASIC 5
9/23
10/28
Sprint 13
Completion
11/11
Sprint 14
Completion
Collaborative Deliverable
Package and VASIC 6
Sprint 11
(9/16 - 9/30)
Sprint 12
(10/3 - 10/14)
Sprint 13
(10/17 - 10/28)
10/21
Sprint 14
(10/31 - 11/11)

## Slide 11: Sprint Forward (Sprint 11)
Complete Modeling engine database structure
Implementation of Modeling engine web service and integration framework design
  Develop SOAP based web service for the Modeling Engine implementation using Java, Jaxws APIs
  Configure SoapUI in local and FTL environment
  Create mock service using SOAPUI

## Slide 12: Questions
?

## Slide 13
Thank you!